## Sheet1
Project Planner
Task Name | To do | Distributed | Deadline | Completed | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Research | ◦Augmented Reality | Week 2 | Week 3 | ü | bar: 2 to 3
| ◦AR used within education | Week 3 | Week 4 | ü | bar: 3 to 4
| ◦Implementation features | Week 4 | Week 6 | ü | bar: 4 to 6
| ◦Udacity | Week 2 | Week 20 | ü | bar: 4 to Project Planner 20
Concept | ◦Objectives | Week 3 | Week 15 | ü | bar: 4 to Project Planner 15
| ◦Refine idea | Week 4 | Week 10 | ü | bar: 4 to 10
| ◦User requirment | Week 3 | Week 15 | ü | bar: 3 to Project Planner 15
Wire frame | ◦Create users expectaions | Week 4 | Week 10 | ü | bar: 4 to 10
| ◦Information architecture | Week 10 | Week 11 | ü | bar: 10 to 11
UI Design | ◦Design prototype | Week 8 | Week 10 | ü | bar: 8 to 10
| ◦Provid mocks | Week 10 | Week 10 | ü | bar: 10
Software planning | ◦Write code | Week 9 | Week 27 | x | bar: 9 to Project Planner 27
| ◦Bring function to life | Week 9 | Week 27 | x | bar: 9 to Project Planner 27
| ◦Connect app to server | Week 20 | Week 27 | x | bar: Project Planner 20 to Project Planner 27
| ◦Intergration and unit testing | Week 20 | Week 27 | x | bar: Project Planner 20 to Project Planner 27
Testing | ◦Testing the code | Week 20 | Week 27 | x | bar: Project Planner 20 to Project Planner 27
| ◦Testing agains user requirnment | Week 20 | Week 27 | x | bar: Project Planner 20 to Project Planner 27